## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
yx6l2VDTokaCd463zq7kipgAEQ8n | Analysing the data | To do | Not started | Medium | Hassan Naik | Hassan Naik | 28/11/2024 |  | 29/11/2024 | false | false
sFdZ_sD8YEaUmnVqVK5mDZgAKqxp | Cleaning the data | To do | Not started | Medium | Hassan Naik | Hassan Naik | 28/11/2024 |  | 29/11/2024 | false | false
QKpT2R4UdUCO_Zsv09DRtZgAFdkG | Acquiring the data | To do | Completed | Low | Hassan Naik | Hassan Naik | 28/11/2024 | 28/11/2024 | 28/11/2024 | false | false | 28/11/2024 | Hassan Naik
N8Cuql3M80KVg6q9CF9taJgAFF_- | Setting the problem statement | To do | Completed | Important | Hassan Naik | Hassan Naik | 28/11/2024 | 28/11/2024 | 28/11/2024 | false | false | 28/11/2024 | Hassan Naik
V1wli_T6SUKjns5-KlUCK5gAAtKe | Visualising the data | To do | Not started | Medium | Hassan Naik | Hassan Naik | 28/11/2024 |  | 05/12/2024 | false | false

## Plan name
Plan name | Final Project
Plan ID | HbyyxMcmp0-bOevLRKvwe5gAFnZt
Date of export | 28/11/2024